# EXL Priority Project Execution Brief — 2026 Marketing Measurement

Audience: EXL program-management and technical-implementation team
Sponsor / decision owner: Stephen Harris, Manager, Growth Operations
Working source of truth: Marketing Tracking Priorities — 2026 Q3
Scope in this brief: Critical Issues Audit, Germany/opt-in data-integrity risk, PSA AppsFlyer evaluation and Branch migration planning, Marketplace Attribution, Iterable CRM deep links, and Event Inventory.

Important: Dates below are a proposed working timetable for EXL execution. A date is not a production commitment unless the relevant Collectors owner and dependency team confirm it in Asana/Jira.

Working-draft convention: TODO marks information that requires system access, current-owner confirmation, or a live audit. EXL should not make production changes until the relevant Collectors owner approves the change.

# Overview

EXL should operate these projects as one coordinated program, not six disconnected tasks. Every workstream must have an Asana project/task, a linked brief, a named owner, a current status, a dependency map, and daily updates.

1. Standard operating contract for every task

EXL responsibilities

Cross-functional dependencies

Required definition of done

2. Proposed timetable

3. Workstream briefs

A. Critical Issues Audit

Request

Brand sequence

In scope

Do not make fixes yet

Required outputs

Required issue-tracker fields

Known-gap starter list

B. Germany launch — minimize litigation and data-integrity risk

Request

Expected result

Dependencies and open questions

QA checklist

C. PSA AppsFlyer evaluation and Branch → AppsFlyer migration

Request

Current context

Evaluation rubric (suggested by AI)

Expected result

Light migration plan if AppsFlyer is approved (suggested by AI)

D. Marketplace Attribution

Request

Flows to inventory

Expected result

Known context to validate

QA checklist

E. Iterable CRM deep-link enablement for PowerPacks

Request

Expected result

Dependency tickets and communications

QA evidence

F. Event Inventory

Request

Platforms in scope

Required inventory columns

4. Q4 priorities

1. Full Audit

2. PowerPacks — Yahoo PowerPacks tracking

3. PSA — Redline App

4. PCGS — Paid preparation

5. GA360

6. Web + App Events Refresh

7. Next phase of SGTM — server tagging

8. Full tracking documentation

9. Next-phase measurement maturity & architecture

# 1. Standard operating contract for every task

### EXL responsibilities

- Load the task into Asana before work starts.

- Add: business outcome, scope, owner, due date, brand, surface, priority, dependencies, risks, acceptance criteria, and links.

- Maintain status, next step, blocker, and ETA daily.

- Post a concise Slack update daily while active; escalate red/urgent issues to Stephen immediately.

- Create Jira tickets for Data, Product/Engineering, IT, security, or other team dependencies as soon as the requirement is understood.

- Maintain a decision log and evidence links.

- Coordinate initial direction check-in, QA review, and final completion review.

- Close the loop by updating documentation, dashboards, event/link inventories, and follow-up tickets.

### Cross-functional dependencies

Technical dependencies must be created early:

- Data models / Lightdash dashboards: Jira on the Data Platform board.

- Product / Engineering web or app changes: Jira in the owning product/engineering project.

- Quantum Metric support: Slack, with the thread linked back to Asana.

- AppsFlyer support: email, with the thread and decision captured in the evaluation record.

- IT / DNS / security / access: Jira or IT service ticket.

### Required definition of done

A task is not complete when EXL finishes its own work. It is complete when:

- the requested output exists;

- the relevant owner has reviewed it;

- QA evidence is attached;

- dependencies and limitations are documented;

- the linked Jira/Asana items are current;

- the final decision or residual risk is recorded; and

- the source-of-truth documentation is updated.

# 2. Proposed timetable

| Workstream | Initial direction check-in | QA / review gate | Target final completion | Key date or constraint |
| --- | --- | --- | --- | --- |
| Critical Issues Audit | Day 2 of each brand week; first scope review before PP fieldwork | Last 2 business days of each brand week; no fixes | Weekly refresh at end of Week 1 PP, Week 2 PSA Grading + Marketplace, Week 3 PCGS; baseline audit closeout after Week 3 | Full comprehensive audit targeted for Q4 |
| Germany / opt-in data integrity | Within 3 business days of kickoff; current sheet update target is 8/21 | Data/Legal/Osano review before Germany launch; test filters, annotations, and regional reporting behavior | Approved risk-reduction plan before launch; exact DE go-live and final sign-off date are TODO | CA and EU opt-in data can make naïve pulls materially incomplete or skewed |
| AppsFlyer evaluation + migration | Current sheet target: 8/20; confirm evaluation rubric and trial plan | Trial QA during PP app release; validate SDK, events, deep links, attribution, BQ/reporting, and cost/support | Evaluation decision before Branch 9/29 EOC; if approved, migration execution target is mid-November | AppsFlyer trial starts 8/17; PP is the first trial surface |
| Marketplace Attribution | Within 3 business days of assignment; review current flow/model map and open questions | Cross-platform flow QA with Marketing/Data; reconcile web/app/CRM and long-lag conversions | Rebaseline with Data if the 8/31 working target cannot be met; final date depends on Data prioritization | Existing reporting work is stalled/partial and requires scope confirmation |
| Iterable CRM deep links | Within 3 business days; confirm PP/GME CRM owner, AF app, domains, and fallback behavior | End-to-end email QA across iOS/Android/web, logged-in/logged-out, installed/not installed, and attribution | Working target 8/31, subject to PP/Engineering/AppsFlyer dependencies | PACK-1135 is stalled and requires prioritization |
| Event Inventory | Start with the Critical Issues Audit kickoff; confirm schema and access before Week 1 fieldwork | Weekly brand-level review; owner validates event names, parameters, links, and examples | Baseline inventory after Week 3, then maintain as a living artifact | Must cover GA4, QM, Branch, AppsFlyer, ad platforms, GTM, app GTM/Firebase, and data layer |

# 3. Workstream briefs

## A. Critical Issues Audit

### Request

Perform a fast audit of platform configurations and tracking to understand the current setup, validate known priorities, identify unknown gaps, and produce a shortlist of work. This is an audit and discovery phase—not a permission to fix production issues.

Note some needs for other priority items may have some overlap with the audit.

### Brand sequence

- Week 1: PowerPacks

- Week 2: PSA Grading and Marketplace

- Week 3: PCGS

- End of each week: refresh the issue tracker and brand report for that week’s focus

- Q4: use the baseline to plan a full, comprehensive audit across all brands and surfaces

### In scope

Audit each applicable surface across:

- Web GTM: containers, workspaces, tags, triggers, variables, consent, publish history, environment separation.

- GA4/Firebase: properties, streams, event names, parameters, conversions, audiences, data freshness, BigQuery export.

- Quantum Metric: projects, session identity, event coverage, funnels, replay usability, cross-domain/app behavior.

- Website data layer: event/schema coverage, CID, transaction IDs, item IDs, value/revenue, consent context, markup/data attributes.

- App measurement: Firebase/GA4, app GTM, Branch, AppsFlyer trial configuration, conversion events, deep links, release QA.

- Paid platforms: Google Ads, Meta, TikTok, StackAdapt, and other active platforms; pixels/CAPI, enhanced conversions, UTMs, macros, event mapping, and account/property ownership.

- CSP and first-party readiness: whether required origins are allowlisted on each paid surface.

- Warehouse/reporting: relevant BigQuery models, Lightdash dashboards, freshness, definitions, joins, filters, and known gaps.

- Documentation: whether the source-of-truth requirement, event inventory, link inventory, and change history exist.

### Do not make fixes yet

- Document the finding.

- Capture severity, evidence, impact, recommendation, and dependency.

- Link the exact page, screen, dashboard, Jira ticket, Confluence page, GitHub file/line, tag, or replay where found.

- Flag anything pressing to Stephen Harris immediately.

- Stephen will work with EXL and the responsible team to decide whether and how to fix it.

### Required outputs

- Audit GSheet / issue tracker with one row per finding.

- Weekly report GDoc or slides summarizing critical issues, low-hanging fruit, major opportunities, and scope limitations.

- Known-gap starter list seeded from the list below.

- Access and evidence log showing what could and could not be validated.

### Required issue-tracker fields

| Field | Requirement |
| --- | --- |
| Finding ID | Stable ID, e.g. PP-GTM-001 |
| Date found / updated | Current date and last validation date |
| Brand | PP, PSA, Marketplace, PCGS, or All |
| Surface | Web, app, CRM, paid, data, dashboard, consent, etc. |
| Platform | GTM, GA4, QM, Branch, AppsFlyer, Meta, Google Ads, BQ, Lightdash, CSP, etc. |
| Finding | Concise statement of the issue/opportunity |
| Severity | Critical / High / Medium / Low / Opportunity |
| Evidence | Exact URL, screenshot if allowed, query, replay, tag, code/file/line, or ticket |
| Business impact | What decision, launch, compliance posture, or reporting is affected |
| Recommendation | Proposed next step; do not imply approval |
| Dependency | Data / Product / Engineering / IT / Legal / Vendor / Marketing |
| Ticket | Jira / Asana / Slack / email thread |
| Owner | Collectors owner and EXL owner |
| Status | Open / Validating / Ready for review / Approved / In progress / Closed |
| Target | Working target or TODO |
| QA evidence | Link to test result, recording, query, screenshot, or sign-off |
| Notes | Assumptions, uncertainty, and access constraints |

### Known-gap starter list

Some issue below are certainly not critical, but we can start building the full list from day one. Just as importantly, I want critical issues to be determined by your discretion, not mine.

| Gap | Why it matters | First audit question | Likely dependency |
| --- | --- | --- | --- |
| CID identity continuity | Breaks the join from paid/CRM click to user, authenticated flow, conversion, and revenue | Does CID persist across landing, login, registration, authenticated pages, web/app transitions, and conversion? | Product/Engineering, CID, Data |
| Conversion and data-layer coverage | Ad optimization, QM, and warehouse joins need standard payloads | Do key intent/conversion events include stable event names, IDs, items, value, revenue, brand, and consent context? | Product/Engineering, Data |
| CSP / pre-launch readiness | A blocked GTM or pixel can turn a launch into click-only measurement | Are GTM, GA4, ad pixels, QM, attribution SDK, and first-party endpoints allowlisted on each launch surface? | IT, Engineering, Security |
| Branch → AppsFlyer decision | Branch EOC and app attribution continuity create a time-bound vendor decision | Can PP trial results answer coverage, cost, deep-link, data, support, and migration questions? | Mobile, Data, IT, vendor |
| Marketplace attribution model | Long-lag multi-step flows make naïve last-touch misleading | Are every flow, conversion definition, lookback, app path, revenue source, and attribution assumption documented? | Data Platform, Marketplace, CRM |
| PowerPacks app tracking | Paid growth needs reliable app identity and conversion data | Are app GTM, Firebase/GA4 events, CID, AppsFlyer, QM, and release QA aligned? | PP mobile, Data, QM, AppsFlyer |
| App event schema | Inconsistent intent events weaken app reporting and optimization | Are app conversion/intent events specified, implemented, and tested? | PSA mobile/P&T, Stephen, Data |
| Audience and suppression automation | Manual suppression increases compliance and operational risk | Are opt-out/do-not-share lists synced reliably to every relevant ad/CRM destination? | Data, Hightouch, Legal/Privacy |
| UTM and link governance | Inconsistent links make channel reporting and deep-link QA unreliable | Are naming, required parameters, platform macros, domains, and fallback paths documented and enforced? | Paid, CRM, Growth Ops |
| Consent-aware measurement | Opt-in regions can look artificially weak if reports treat missing consent as zero | Do reports identify consent status, coverage, exclusions, and directionality? | Data, Legal, Osano, Marketing |
| Web/app parity | Different systems can report different users, sessions, and conversions | Which source is authoritative for each metric, and how are discrepancies explained? | GA4, QM, Branch/AF, Data |
| PCGS / PSA Video Games parity | Less mature surfaces increase risk as paid programs expand | What is implemented, what is owned, and what is missing relative to PSA? | Brand teams, P&T, Data |
| Cross-brand identity | No unified layer limits cross-brand attribution and personalization | Which identifiers are shared, and where must brand/source be preserved? | CID, Data, CRM |
| SGTM and legacy cleanup | Partial server-side architecture and legacy events increase maintenance risk | Which events are loader-only, client-side, server-side, duplicated, or unowned? | Platform Engineering, IT, Data |

## B. Germany launch — minimize litigation and data-integrity risk

### Request

Provide thought partnership and a practical reporting-control plan before the Germany launch. California and EU regions require opt-in consent, so naïve data pulls may undercount or skew performance. The goal is to reduce the chance that incomplete consented data is interpreted as full-population truth.

### Expected result

Produce a reviewed plan that includes:

- a consent-aware measurement taxonomy;

- default filters or report views for affected regions;

- visible annotations/warnings on dashboards and recurring reports;

- a distinction between observed, consented, modeled, and directional metrics;

- rules for excluding or separately presenting CA/EU data in ad hoc analyses;

- monitoring for consent coverage, event volume, match rate, and regional anomalies;

- recommendations for longer-term modeling, such as consent-mode-aware modeling, server-side signals, MMM, or incrementality testing;

- a decision log identifying what is safe for launch and what remains TODO.

### Dependencies and open questions

- Data: DPE-5142, “Planning for Opt-In Data”; confirm owner, model scope, and Lightdash/report impact.

- Legal / Privacy / Osano: confirm required consent behavior, regional definitions, and approved wording.

- Product / Engineering: confirm consent event and region fields exist on every relevant surface.

- Marketing: confirm which dashboards and decisions require regional reporting.

- TODO: exact Germany launch date, report inventory, consent field names, region source of truth, minimum acceptable coverage, and final approver.

### QA checklist

- Test an opted-out/unknown/opted-in user path where permitted.

- Confirm region and consent status are available in the event/model used for reporting.

- Confirm default filters do not silently remove users from the denominator.

- Confirm report annotations survive copy/export and are visible to non-authors.

- Confirm dashboard values reconcile to a known sample and that gaps are labeled directional.

## C. PSA AppsFlyer evaluation and Branch → AppsFlyer migration

### Request

Evaluate Branch against AppsFlyer, provide a structured recommendation, create a reusable evaluation rubric, and produce a light migration plan that allows work to start immediately if AppsFlyer is approved.

### Current context

- AppsFlyer trial begins 8/17/2026 on the PowerPacks app.

- Branch end-of-contract date is 9/29/2026; the decision must be made in advance of that date to avoid an unplanned renewal or a rushed migration.

- The first evaluation surface is PowerPacks; PSA and PCGS app implications must be included.

- Relevant current tickets include PGX-4934, DPE-5145, IT-120296, and IS-11560.

### Evaluation rubric (suggested by AI)

Score each platform 1–5, attach evidence, and distinguish confirmed fact from vendor claim.

| Dimension | Questions to answer |
| --- | --- |
| Attribution coverage | Can it support required web/app campaign and conversion use cases? |
| Deep links / deferred deep links | Do email, paid, QR, and cross-device flows open the right app/screen with reliable fallback? |
| App event support | Can required Firebase/GA4/app GTM events, parameters, IDs, and revenue be captured? |
| Identity | Can CID and app/device identifiers be reconciled without creating unsafe or duplicate identity? |
| Reporting / warehouse | Can data be exported to BigQuery or otherwise modeled with usable grain, history, and latency? |
| Privacy / consent | Does the platform support Collectors’ consent, regional, and data-minimization requirements? |
| Ad-platform integrations | Can Google, Meta, TikTok, and other priority channels receive the required signals? |
| CRM support | Can Iterable/SFMC links and downstream conversion behavior be validated? |
| QA / observability | Are there test tools, logs, replay, alerting, and reliable release-validation workflows? |
| Cost / contract | What is the full cost at current and projected event/user volume, including Stape/data impact? |
| Migration effort | What SDK, DNS, app-release, data-model, reporting, and historical-join work is required? |
| Vendor support | Response time, implementation help, documentation, escalation path, and account support |

### Expected result

- A completed Branch vs AppsFlyer scorecard with evidence and unresolved questions.

- A recommendation: AppsFlyer, Branch, retain/extend Branch, or defer—subject to Stephen and leadership approval.

- A decision log with business, technical, privacy, and timeline rationale.

- A light migration plan that can start immediately after approval.

- A full-plan backlog outline for the remaining migration work.

### Light migration plan if AppsFlyer is approved (suggested by AI)

- Confirm decision, scope, owners, and app release window.

- Complete AppsFlyer security review and IT/DNS work.

- Confirm app identifiers, domains, OneLink/deep-link structure, consent behavior, and environment strategy.

- Finalize event and parameter mapping from Branch/Firebase/GA4/app GTM to AppsFlyer.

- Implement or validate the PSA app SDK work and preserve historical Branch data references.

- Validate PP trial results and confirm release timing.

- Create Data tickets for historical break handling, new ingestion, models, and dashboards.

- Create CRM/deep-link test cases for email and paid retargeting.

- Run parallel QA where practical: install, open, deep link, deferred deep link, login, registration, conversion, revenue, and app/web handoff.

- Define cutover, rollback, Branch archive/renewal decision, and post-cutover monitoring.

## D. Marketplace Attribution

### Request

Verify that documented Marketplace flows are complete, review the attribution/modeling approach, and recommend improvements—large or small—even if the current model remains last-touch.

### Flows to inventory

At minimum, map:

- Paid click → web landing → sign-in/registration → marketplace/vault intent → submission or listing → offer/eBay action → sale/revenue.

- CRM email/push → web or app deep link → authenticated action → marketplace conversion.

- PSA web → PSA app transition, including My Collection and app-forced links.

- Direct or organic entry where paid/CRM source may be absent.

- Vault intent changes and long-lag downstream marketplace outcomes.

- eBay BIN/auction listing, sale, and GMV/revenue events.

- PSA Partner Offer acceptance and other offer flows.

- Web-only GA4 reporting versus app/Branch/AppsFlyer visibility.

### Expected result

- Current-state flow diagram and event/conversion inventory.

- Attribution matrix: source, identifier, conversion, lookback, reporting grain, and known blind spots.

- Review of current last-touch assumptions and where they are directionally useful versus decision-grade.

- Recommended changes ranked by impact and effort.

- Data/Jira backlog for model, dashboard, and event changes.

- QA plan covering web, app, CRM, paid, identity, and revenue reconciliation.

### Known context to validate

- DPE-5146 is the current Marketplace reporting priority and has been described as stalled/partial.

- Marketplace reporting needs additional conversions beyond submission: vault, PSA Offers, eBay listing/sale, and GMV/revenue.

- CRM and app conversions cannot be assumed to be covered by the existing web-only GA4 attribution model.

- Current data discussions include marketing-touch and conversion tables, long conversion windows, and app/web source-of-truth questions.

### QA checklist

- Test a known paid click through each supported conversion path.

- Test CRM email links that open web and app.

- Confirm CID or approved identifier is present at each join point.

- Reconcile event counts and conversion counts between source platform, BigQuery model, and Lightdash.

- Confirm lookback windows and revenue timing are documented.

- Document cases where privacy, consent, missing CID, or cross-device behavior prevents deterministic attribution.

## E. Iterable CRM deep-link enablement for PowerPacks

### Request

Enable the PowerPacks team to send Iterable CRM emails with app deep links by configuring and validating the AppsFlyer path.

### Expected result

- Confirm the GME/PP Iterable owner and sending process.

- Confirm AppsFlyer app, OneLink/template, domains, branding, and fallback behavior.

- Define link parameters and attribution requirements.

- Produce an implementation and QA checklist.

- Validate installed-app, non-installed-app, web fallback, iOS, Android, logged-in, and logged-out paths.

- Document results and known limitations for PP Marketing.

### Dependency tickets and communications

- PACK-1135: PP Iterable CRM push and deep-link enablement.

- AppsFlyer vendor support: email thread linked in Asana and decision log.

- PP/Engineering: app routes, release timing, and event/identity behavior.

- IT/Security: domains and vendor review if required.

- Data: reporting and downstream attribution model requirements if new events/fields are introduced.

### QA evidence

For each test, record email/template, link, device/OS, app-installed state, user state, destination screen, attribution result, and screenshot/log/replay evidence where permitted.

## F. Event Inventory

### Request

Document all existing events across platforms and their relevant data layers. This can be performed in tandem with the Critical Issues Audit and should become a living source of truth.

### Platforms in scope

- Web data layer and GTM.

- GA4 / Firebase.

- Quantum Metric.

- Branch.

- AppsFlyer.

- Google Ads, Meta, TikTok, StackAdapt, and other active ad platforms.

- App GTM and mobile event schemas.

- BigQuery models and Lightdash dashboards that depend on the events.

- Relevant CRM/Iterable/SFMC link and conversion events.

### Required inventory columns

| Column | Requirement |
| --- | --- |
| Event name | Exact platform event name and common canonical name |
| Platform | GA4, QM, Branch, AppsFlyer, ad platform, GTM, Firebase, CRM |
| Brand / surface | PSA web, PSA app, Marketplace, PCGS, PP web, PP app, etc. |
| Trigger | User action, page state, backend state, campaign, or system trigger |
| Parameters / attributes | Names, types, examples, required/optional, PII classification |
| Identity | CID, client ID, device ID, session ID, transaction ID, or other key |
| Conversion status | Primary conversion, secondary intent, diagnostic, or non-conversion |
| Source tag / code | GTM tag, app code, SDK, or server-side route |
| Page / screen | Exact URL, route, app screen, or TODO |
| QM replay / funnel | Exact replay, funnel, or TODO |
| GitHub evidence | Repo/file/line link or TODO |
| Data layer sample | Pretty web push or app payload sample |
| BQ model | Dataset/table/model and downstream join |
| Lightdash/dashboard | Link and metric/field dependency |
| QA status | Not tested / tested / issue / approved |
| Owner | Marketing, P&T, Data, vendor, or TODO |
| Notes | Consent, dedupe, known gap, deprecation, or migration note |

Replace placeholders only after validating the current approved schema. Do not copy real customer identifiers into the inventory.

# 4. Q4 priorities

## 1. Full Audit

Request: Expand the initial brand-by-brand Critical Issues Audit into a comprehensive audit across all relevant brands, surfaces, platforms, configurations, tracking, consent controls, data layers, models, dashboards, and documentation.

Expected result:

- A single living audit tracker with one row per finding, stable IDs, severity, evidence links, business impact, recommendation, owner, dependency, ticket, status, and QA evidence.

- Brand/surface coverage for PSA, Marketplace/Vault, PowerPacks, PCGS, and any additional in-scope properties confirmed during onboarding.

- A final report separating critical issues, launch/compliance risks, low-effort fixes, structural opportunities, and items that could not be validated because of access or data limitations.

- A prioritized 2027 backlog with effort, sequencing, and recommended owners.

Dependencies: Growth Ops, Marketing, P&T, Data, Product/Engineering, IT/Security, Legal/Privacy, QM, AppsFlyer/Branch, ad platforms, and brand owners. Do not make fixes as part of the audit unless separately approved.

## 2. PowerPacks — Yahoo PowerPacks tracking

Request: Prepare, validate, and document tracking for the Yahoo PowerPacks launch and related paid/owned flows, based on the GameStop PowerPacks setup.

Expected result:

- Confirmed measurement plan for Yahoo PP landing, click-through, sign-in/registration, app or web handoff, purchase/conversion, and downstream reporting.

- Validated UTM/link-tagging requirements, CID continuity, data-layer events, GA4/Firebase, GTM, QM, AppsFlyer, Google Ads, and Meta behavior as applicable.

- Explicit treatment of any iframe, cross-domain, consent, or attribution limitations; do not assume parent-page tracking captures iframe behavior.

- Launch-readiness checklist, QA evidence, open-risk log, and post-launch monitoring plan.

Dependencies: PP Marketing/GME, Product/Engineering, Data, paid media, QM, AppsFlyer, IT/DNS/CSP, and any Yahoo or partner implementation owner. Create tickets for web/app changes and data-model/dashboard updates early.

## 3. PSA — Redline App

Request: Define and execute the tracking and measurement work needed for the PSA Redline App initiative. Confirm the product scope and launch/release window before implementation.

Expected result:

- A surface and user-flow map covering install/open, authentication, key Redline actions, conversion events, revenue or transaction context, and app/web handoffs.

- Event and parameter requirements aligned to the common event schema and current app conventions.

- Confirmed treatment of CID, consent, Firebase/GA4, app GTM, QM, AppsFlyer/Branch, and downstream BigQuery/Lightdash dependencies.

- Product/Engineering Jira tickets, release QA plan, post-release monitoring, and updated event inventory.

TODO: Confirm Redline App business outcome, named Product/Engineering owner, app package/platform scope, launch date, and whether the work is a net-new surface or a refactor of the existing PSA app.

## 4. PCGS — Paid preparation

Request: Prepare Google Ads and Meta tracking for PCGS paid campaigns.

Expected result:

- Confirmed Google Ads and Meta account/property ownership, pixels/tags, conversion actions/events, enhanced-conversion or server-side requirements, UTMs/macros, and consent behavior.

- Page/data-layer and CSP readiness validated for every campaign landing surface.

- Naming and link-tagging conventions documented and tested before launch.

- QA evidence for browser events, downstream platform receipt, deduplication where applicable, and reporting reconciliation.

- A launch checklist and open-dependency list for PCGS Marketing, Paid, Product/Engineering, Data, IT/Security, and QM.

Dependencies: PCGS Marketing, Dan Gaughan, Jenna Connolly, PCGS web/product owners, Data, IT/Security, and ad-platform support as required.

## 5. GA360

Request: Evaluate whether Collectors needs GA360 and identify credible ways to reduce cost without creating unacceptable measurement, governance, reporting, or data-access risk.

Expected result:

- Current-state inventory of GA4 properties, streams, users, exports, integrations, audiences, BigQuery usage, reporting dependencies, and any 360-only capabilities in active use.

- Decision framework comparing GA360 against standard GA4 plus existing BigQuery, Lightdash, QM, and other tooling.

- Savings scenarios with assumptions, one-time migration effort, recurring cost impact, operational risk, and capabilities lost or retained.

- Recommendation: retain, reduce scope, renegotiate, or move to a standard GA4 architecture—subject to Finance, Data, Marketing, and leadership approval.

- Transition plan and validation checklist if savings require property, export, audience, or reporting changes.

Dependencies: Marketing Intelligence, Growth Analytics, Data Platform, Finance/Procurement, Google/vendor support, and dashboard/report owners. Do not change licensing or production configurations from the evaluation alone.

## 6. Web + App Events Refresh

Request: After the Event Inventory is complete, identify events that do not align with the common event schema or that would benefit from platform-specific conventions. Work with Stephen to create and execute a refactoring plan.

Expected result:

- Gap analysis showing canonical event name, current platform-specific name, parameters, identity fields, consent context, owner, and downstream use.

- Refactoring plan ranked by business impact, implementation effort, risk, and dependency.

- Mapping of affected events to BigQuery models and current Lightdash and QM dashboards/funnels.

- Product/Engineering tickets for web and app changes; Data tickets for model and Lightdash updates; QM Slack requests for event/funnel/dashboard updates.

- Pre/post-change QA covering payloads, deduplication, identity continuity, consent behavior, platform receipt, models, dashboards, and QM outputs.

- Refreshed Event Inventory with deprecation dates, replacement events, migration status, and final evidence.

Dependency rule: No event should be renamed or deprecated until all known downstream uses are mapped and a migration/compatibility plan is approved.

## 7. Next phase of SGTM — server tagging

Request: Extend the first-party loader and Stape-hosted server-side GTM architecture toward a controlled server-tagging model. The long-term goal is one web-app beacon per event, with SGTM enriching from BigQuery and forwarding to relevant platforms – but this is not expected by EOY (and certain pixels may remain semi-redundantly on-page where client-side features or third-party-cookie advantages justify it). For 2026, focus on a practical first phase rather than full replacement of every client-side pixel.

EOY target: Have Facebook Conversions API and Google Ads server-side tagging working for all brands, subject to platform, consent, engineering, and data readiness.

Expected result:

- Current-state map of first-party loader, Stape containers, domains, event routes, client-side tags, server-side tags, enrichment sources, and duplicate-signal risks.

- Target-state architecture and phased implementation plan, including what remains client-side and why.

- Brand-by-brand readiness assessment for Meta CAPI and Google Ads server tagging.

- Required GTM, Product/Engineering, Data, IT/DNS/CSP, consent, and ad-platform tickets.

- Test plan for event parity, deduplication, match quality, latency, consent behavior, failure handling, and rollback.

- Monitoring and cost/quota plan for Stape and downstream platforms.

Dependencies: Platform Engineering, Growth Ops, Data Platform, IT/Security, Legal/Privacy, Meta, Google Ads, Stape, and each brand’s web/app owners.

## 8. Full tracking documentation

Request: Create a durable, cross-brand tracking documentation set that makes implementation and audit work repeatable.

Required coverage:

- CSP requirements by brand, surface, environment, and vendor endpoint.

- Markup, page-component, route, and data-layer dependencies.

- Event and parameter definitions, identity fields, consent behavior, and ownership.

- GTM/SGTM routing, ad-platform mappings, QM dependencies, and app equivalents.

- BigQuery models, Lightdash dashboards, and known reporting dependencies.

- Change-management rules, QA evidence, deprecation history, and source links to Jira/GitHub/Confluence.

Expected result: A linked documentation index, brand/surface pages, current architecture diagram or map, dependency matrix, and maintenance owner/cadence. Documentation must distinguish current state, target state, and TODOs.

## 9. Next-phase measurement maturity & architecture

Request: Provide thought partnership on the overall measurement architecture and practical paths toward multi-touch attribution (MTA) and marketing-mix modeling (MMM).

Expected result:

- Current-state architecture assessment covering identity, consent, event collection, web/app parity, attribution, warehouse modeling, dashboards, server-side tagging, CRM, and paid-platform activation.

- Options for improving measurement maturity, with benefits, limitations, implementation effort, data requirements, and decision use cases.

- Clear distinction between deterministic attribution, modeled attribution, incrementality testing, MTA, and MMM; identify where each is appropriate and where it should not be treated as truth.

- Recommended sequence of foundational work before MTA/MMM, including event governance, CID/identity continuity, consent-aware data treatment, conversion definitions, experiment design, and data-quality monitoring.

- Architecture discussion with Stephen and relevant Marketing, Data, Product/Engineering, and Finance stakeholders; capture decisions and unresolved questions.

Expected result is a decision framework and roadmap—not a promise to deploy MTA or MMM in Q4.